## 关于
关于此甘特图
使用此甘特图模板使项目可视化，并跟踪项目。首先，在“里程碑描述”部分中输入你正在处理的任务，然后输入每个任务的详细信息。数据将自动进行更新，你可轻松插入新任务或使用滚动条滚动浏览日程表。
• 使用“进度”列通过添加百分比数字来添加已完成的项目量 • 在“开始日期”列添加项目的启动日期。 • 通过在“天数”列中填写完成项目所需的天数来完成计算。

## 绿色
AutonomousQuadruped
RoboDog
Team22
Start Date： | 2023-06-19 | [9 empty] | Rolling Increment | [5 empty] | 0
Milestone Marker: | 1 |  |  | 6月 | [13 empty] | 7月 | [34 empty] | 8月
 | time axis 2023-06-19 to 2023-08-13
Milestone Description | Responsible Person | Start | Number of Days | time axis 2023-06-19 to 2023-08-13
General work | All | 2023-07-13 | 18
Final Test and Debug | All | 2023-07-13 | 7
Prepare documentation and Presentation | All | 2023-07-17 | 14
State Machine | Yankun Wei | 2023-06-19 | 9
Search Information | Yankun Wei | 2023-06-19 | 4
Implementation: Node Statemachine | Yankun Wei | 2023-06-22 | 6
Perception Pipeline | Yankun Wei, Hao Guo | 2023-06-19 | 16
Search Information | Yankun Wei, Hao Guo | 2023-06-19 | 5
Implementation: Node Perception | Yankun Wei, Hao Guo | 2023-06-22 | 13
Depth to Pointcloud | Yankun Wei | 2023-06-26 | 1 | bar: 2023-06-26
Pointcloud to voxelgrid | Hao Guo | 2023-07-03 | 1 | bar: 2023-07-03
Path Planner | Shaoxiang Tan, Hanyu Li, Hao Guo | 2023-06-19 | 27
Search Information | Shaoxiang Tan | 2023-06-19 | 7
Determine the data format of path points | Shaoxiang Tan, Hanyu Li | 2023-06-24 | 1 | bar: 2023-06-24
Implementation: Node Pathplanner | Shaoxiang Tan, Hanyu Li, Hao Guo | 2023-06-24 | 22
Implementation in predefined voxelgrid | Shaoxiang Tan | 2023-07-04 | 1 | bar: 2023-07-04
Implementation in voxelgrid from perception | Hanyu Li, Hao Guo | 2023-07-13 | 1 | bar: 2023-07-13
Trajectory Planner | Hanyu Li, Yujie Guo | 2023-06-19 | 27
Search Information | Hanyu Li, Yujie Guo | 2023-06-19 | 7
Determine the data format of path points | Shaoxiang Tan, Hanyu Li | 2023-06-24 | 1 | bar: 2023-06-24
Implementation: Node Trajectory Planner | Hanyu Li, Yujie Guo | 2023-06-24 | 22
Implementation with predefined path points | Hanyu Li | 2023-07-05 | 1 | bar: 2023-07-05
Implementation with path points from Pathplanner | Yujie Guo | 2023-07-13 | 1 | bar: 2023-07-13
Position Controller | Hanyu Li, Yujie Guo | 2023-06-19 | 27
Understand the control method | Hanyu Li, Yujie Guo | 2023-06-19 | 7
Implementation with trajectory | Yujie Guo | 2023-06-24 | 22
若要添加更多数据，请在此行上方插入新行

## 蓝色
项目：蓝色
Contoso, Ltd.
Gurpreet Bawa
项目开始日期： | 2023-06-16 | [10 empty] | 滚动增量： | [5 empty] | 13
里程碑标记： | 1 | 1 |  |  | 6月 | [6 empty] | 7月 | [27 empty] | 8月
 | time axis 2023-06-29 to 2023-08-23
里程碑描述 | 责任人 | 进度 | 开始 | 天数 | time axis 2023-06-29 to 2023-08-23
标题 1
任务 1 |  | 25% | 2023-06-19 | 3
任务 2 |  |  | 2023-06-24 | 1
任务 3 |  | 50% | 2023-06-16 | 10
任务 4 |  |  | 2023-07-09 | 1 | bar: 2023-07-09
任务 5 |  | 10% | 2023-06-25 | 6
标题 2
任务 1 |  | 60% | 2023-06-25 | 13
任务 2 |  | 50% | 2023-06-26 | 9
任务 3 |  | 33% | 2023-07-04 | 11
任务 4 |  |  | 2023-07-13 | 1 | bar: 2023-07-13
任务 5 |  |  | 2023-07-14 | 24
标题 3
任务 1 |  |  | 2023-07-04 | 4
任务 2 |  |  | 2023-07-08 | 14
任务 3 |  |  | 2023-07-24 | 6
任务 4 |  |  | 2023-08-06 | 3
任务 5 |  |  | 2023-07-29 | 19
标题 4
任务 1 |  |  | 2023-07-26 | 15
任务 2 |  |  | 2023-07-18 | 5
任务 3 |  |  | 2023-09-07 | 5
任务 4
任务 5
若要添加更多数据，请在此行上方插入新行

## 紫色
项目：紫色
Contoso, Ltd.
Hayden Cook
项目开始日期： | 2023-06-16 | [10 empty] | 滚动增量： | [5 empty] | 13
里程碑标记： | 1 | 1 |  |  | 6月 | [6 empty] | 7月 | [27 empty] | 8月
 | time axis 2023-06-29 to 2023-08-23
里程碑描述 | 责任人 | 进度 | 开始 | 天数 | time axis 2023-06-29 to 2023-08-23
标题 1
任务 1 |  | 25% | 2023-06-19 | 3
任务 2 |  |  | 2023-06-24 | 1
任务 3 |  | 50% | 2023-06-16 | 10
任务 4 |  |  | 2023-07-09 | 1 | bar: 2023-07-09
任务 5 |  | 10% | 2023-06-25 | 6
标题 2
任务 1 |  | 60% | 2023-06-25 | 13
任务 2 |  | 50% | 2023-06-26 | 9
任务 3 |  | 33% | 2023-07-04 | 11
任务 4 |  |  | 2023-07-13 | 1 | bar: 2023-07-13
任务 5 |  |  | 2023-07-14 | 24
标题 3
任务 1 |  |  | 2023-07-04 | 4
任务 2 |  |  | 2023-07-08 | 14
任务 3 |  |  | 2023-07-24 | 6
任务 4 |  |  | 2023-08-06 | 3
任务 5 |  |  | 2023-07-29 | 19
标题 4
任务 1 |  |  | 2023-07-26 | 15
任务 2 |  |  | 2023-07-18 | 5
任务 3 |  |  | 2023-09-07 | 5
任务 4
任务 5
若要添加更多数据，请在此行上方插入新行